## Sheet1
MICRO LABS LIMITED
Gate Entry Application
|  |  |  | Date | Remarks
Architecture | Web Application | Front End | Java |  | Technology Study
|  | Back End DB | MS SQL
Software | Ecllipse 6.0 | Back End Activities | DB Design |  | New Technology JSF
| TOM CAT 6.0.36 |  | Table Creation |  | Java Server Faces
Login Page | Main | Fields |  | Date | Remarks
| User details | Name | Design | 2013-10-01 | Done
Password
Location
| Forgot Password |  | Design | 2013-11-01 | Done
| Help |  | Design | 2013-11-01 | Done
Home Page | Menus |  | Design | 16/1/2013
| Dash Board (Current Day) | Vistors | Design | 16/1/2013
|  | Materials Outward | Design | 16/1/2013
Home Page | Full | No broken Links |  | 20/1/2013
DataBase | Structures |  |  | 19/1/2013
| Table Creations |  |  | 19/1/2013
Menu | Main Menu | Sub-Menu | Sub-Sub-Menu | Date | Remarks
Gate Inward
|  | Visitors | Screen Design | 17/1/2013
|  |  | Scheduled |  | e-Micro Integration
|  |  | Un-Scheduled | 20/1/2013
Image Capture
|  |  | Pass Print |  | Dot Matrix output
|  | Materials | With PO |  | SAP Integration
Without PO
Returnable
Stock Transfer
Sub Contracting
Gate Outward
Security Entry
|  | Materials | General
Returnable Closure
|  | Excise Invoice |  |  | SAP Integration
Sub Contracting
Sub Transfer
Reports
Visitors
|  | Materials | Inward
Outward
Sub Contracting
Returnable
| Admin | User
|  | Access | Menu Control |  | Grouping module
|  |  | Mail Control |  | e-mail module